HIGH DESERT

Funding Strategy & Pipeline — v3

June 2026 · Companion to Business Plan v11 · Deadlines verified June 10, 2026 — reconfirm at each portal before submitting

Resiliency means no single funder — public or private — can bend this. Dues fund the core; everything else is additive, diversified, capped, and disclosed.

This document maps every viable funding source for High Desert, sequenced for speed and built for resiliency. Private funding leads; a separate government track follows, on High Desert’s transparency terms. The Master Case for Support and the Grant Applications Pack are companions — the reusable narrative and the ready-to-send letters.

# 01 — Act This Month: the Critical Path

| THE GATE | Almost every institutional funder requires either a 501(c)(3) determination letter or a fiscal sponsor. High Desert’s determination is months away — so a fiscal sponsorship agreement is the single unlock for 2026 money. Securing one is this month’s most important funding task. |
| --- | --- |

## Verified Time-Sensitive Windows (as of June 10, 2026)

| Opportunity | Deadline | Status & Move |
| --- | --- | --- |
| OCF Fall Community Grants (up to $40K; typical $15–20K) | June 23, 2026, 5pm — new-applicant account form by June 18 | Open now; accepts fiscal sponsorship (materials due with application) and requires Oregon DOJ registration. Honest call: feasible only if a sponsor signs within days. Register the MyOCF account by June 18 regardless — it costs nothing and unlocks the Spring 2027 cycle (apps Dec–mid-Jan, which prioritized small rural and culturally responsive organizations in 2026). |
| Roundhouse Foundation — Fall Open Call | Window open June–August 2026 | Open now. Sisters-based, rural Central Oregon is the home turf, and they explicitly fund fiscally-sponsored projects. This is the flagship 2026 target. Decisions ≈ 8–12 weeks. |
| Roundhouse Foundation — Small Grants | Rolling LOIs through Nov 30 | Open now. Entry-level grassroots grants; the fastest credible institutional dollars available. Submit the LOI (in the Grant Pack) as soon as sponsorship is signed. |
| Ford Family Foundation — Good Neighbor / Technical Assistance | Rolling, no deadline | Open, but call the program officer first — see the eligibility note in §02. TA grants (orgs under $1M budget) can fund formation and fundraising capacity. |

## Fiscal Sponsor — Decision This Week

- What it is — an established 501(c)(3) receives restricted grants and donations on High Desert’s behalf for a 5–10% admin fee until the determination letter arrives. Roundhouse and OCF both accept sponsored applicants by policy.

- First call: Connect Central Oregon — a regional capacity-building nonprofit whose explicit role is incubating and partnering with Central Oregon organizations — either a direct sponsor or the best-positioned source of a referral to one. Other local candidates come through Compass’s and Herringbone’s board networks. Ask: “would you sponsor a six-to-twelve-month pass-through while our determination is pending, or point us to who would?”

- National fallbacks — established multi-project sponsors (e.g., Social Good Fund and similar 501(c)(3) sponsor organizations) sign quickly at standard fees if no local option lands within two weeks.

- Exit built in — the agreement should state that grants and donor relationships transfer to High Desert upon determination.

## Also This Month (no sponsor needed)

- Oregon DOJ Charitable Activities registration — required before soliciting; file with formation paperwork

- MyOCF nonprofit account — by June 18

- Roundhouse introduction — email or call; they welcome pre-application contact, and Sisters is a short drive: go in person

- Founding Supporters campaign design — individual giving launches with the platform in October; receipts note determination pending, deductibility retroactive

# 02 — Private Funding (Primary Track)

## Tier 1 — Regional Anchors (2026 entry)

| Funder | Mechanics (verified) | Fit & Strategy |
| --- | --- | --- |
| Roundhouse Foundation (Sisters, OR) | Small Grants: rolling LOIs Jan–Nov 30, 8–12 wk decisions. Open Call: spring (Jan–Mar) and fall (Jun–Aug) cycles. Grants commonly $10K–$100K; multi-year possible. Funds 501(c)(3)s, fiscally-sponsored projects, Tribal governments. | Best fit in the country for this project: rural Central Oregon focus, arts/community/education lenses, comfort with grassroots innovation. Sequence: Small Grant LOI in July (launch capacity, ~$12.5K) → Fall Open Call application in August (flagship two-year program, ~$48K). One relationship, two asks, properly spaced. |
| Oregon Community Foundation | Community Grants: two cycles/yr; Fall 2026 closes June 23; Spring 2027 apps Dec–mid-Jan, decisions ≈ May. Up to $40K, one year. Fiscal sponsorship accepted. Two-cycle sit-out after a win. | Statewide credibility anchor; Central Oregon regional staff in Bend — build the relationship now. Spring 2027 is the planned entry (small-rural priority cycle); June 23 only if sponsorship closes immediately. Also: OCF’s donor-advised funds discover grantees through program staff — the relationship compounds. |
| The Ford Family Foundation (Roseburg) | Rolling applications, no deadlines. Good Neighbor grants (flexible community initiatives) and Technical Assistance grants (orgs under $1M; consultants, training). Awards commonly $5K–$25K+. | Eligibility nuance, honestly: their “rural” means ≤35K population and not adjacent to a 50K+ metro — Redmond alone is borderline on both. The credible frames: (a) Central Oregon’s clearly-rural towns (Sisters, La Pine, Madras, Prineville, Terrebonne, Culver) as the platform’s service horizon; (b) a TA grant for organizational capacity benefiting that rural footprint. Call the program officer before applying — they invite it, and the call settles eligibility in ten minutes. |

## Tier 2 — Statewide Foundations (2027, with determination letter)

- The Collins Foundation — Oregon-wide; $5K–$100K; project and operating support; accessible process. Strong community-welfare fit. Apply after determination, with launch results in hand.

- Meyer Memorial Trust — large Oregon funder organized around equity and community power; annual funding opportunities. Moderate fit via community-voice and belonging framing — watch the 2027 opportunity announcements and apply only if the portfolio language genuinely matches.

- Small Oregon trusts (Autzen Foundation, Rose E. Tucker Charitable Trust, and peers) — modest general-purpose grants, typically low five figures or less, light applications. Good 2027 fill-ins once determined; verify current guidelines at application time.

## Tier 3 — National Civic-Information Funders (watch list + one partnership play)

National civic-tech and local-news philanthropy is real money but episodic, and High Desert is not a newsroom — so this tier is played through positioning and partnership, not cold applications:

- Press Forward (pooled fund + ~31 local chapters) — periodic open calls — past rounds funded small local outlets (~$100K unrestricted) and news infrastructure ($500K–$1.5M). The live opportunity is a joint concept with Redmond Compass: Compass as the original-reporting outlet, High Desert as the verified civic-distribution layer — “community information system” is exactly the language their rural cohorts use. Action now: create the JustFund organizational profile (coalition funders browse it between open calls) and watch announcements.

- Adjacent funders (Siegel Family Endowment, Democracy Fund, Knight, and the New_ Public ecosystem) — mostly invitation-only or city-bound; treat as relationship and visibility targets — the open-sourced governance model and the transparency reports are the credibility artifacts that get noticed — not as pipeline.

## Tier 4 — Hyper-Local & Corporate (small, fast, trust-building)

Small checks that arrive quickly and — more importantly — put recognizable local names behind the founding story. In a region wary of outside money, a local co-op’s logo is worth more than its dollar amount:

- Central Electric Cooperative (HQ Redmond) — member-owned co-op and an active charitable grantmaker (roughly $950K in recent annual giving). The philosophical kinship is real — a cooperative funding commons infrastructure. Approach by direct inquiry with the one-page case; verify their current program mechanics when you call.

- First Interstate Bank foundation giving (Redmond branch footprint) — ongoing local-community grants; small, fast, brand-credible. Verify the current cycle.

- Mid Oregon Credit Union, BendBroadband/TDS community giving, local Rotary and Kiwanis — $500–$5K sponsorships, especially for events, the internship showcase, and Spanish-language outreach.

- City of Redmond / Visit Redmond / REDI / Deschutes County discretionary programs — more civic legitimacy than money; pursue selectively in 2027 under the government-transparency posture.

# 03 — Government Funding (Separate Track, 2028+)

| POSTURE | Government money is accepted — sequenced after local trust is established, used for infrastructure-scale work only, never core operations, and wrapped in radical transparency: every dollar, condition, and reporting obligation published. Refused outright if any condition touches the foundational commitments. |
| --- | --- |

## The Honest Federal Landscape (verified June 2026)

- Digital Equity Act programs — terminated — all three programs ($2.75B) were cancelled by the administration in May 2025. Do not plan around them; if reinstated by litigation or a future Congress, the Competitive program would be a strong fit — watch only.

- USDA Community Connect (FY2026 open) and Distance Learning & Telemedicine — funded (~$44M combined) but deployment- and telehealth-shaped — not a platform fit today. Relevant later as a Warm Springs infrastructure pathway.

- Tribal broadband (NTIA TBCP) — no open window in 2026; awarded tribes are in buildout. The 2029+ Warm Springs co-application runs through BEAD tribal set-asides and the Oregon Broadband Office instead — begin that relationship in 2027–28.

- USDA ReConnect — facing proposed cuts; monitor, don’t plan on it.

## State & Local (small, mission-specific, 2027–28)

- Oregon Heritage Commission grants — the natural funder for the historical-archive feature (Phase 2) — apply only after Warm Springs consultation shapes the archive’s design

- Oregon Humanities — periodic program grants for community conversation and public dialogue — fits the listening-session and civic-dialogue work

- Deschutes Cultural Coalition (Oregon Cultural Trust pass-through) — small annual grants ($1–3K) for culture and heritage projects — easy, local, archive- and event-adjacent

- Oregon Broadband Office — the standing relationship for the Connect program and the Warm Springs horizon — open it in 2027; state broadband deployment subgrants and tribal set-asides both route through this office

## The Connect Infrastructure Track (2028+, deployment-shaped)

High Desert Connect — rural connectivity pilots and the Tribal Digital Sovereignty Program — opens a distinct government lane. Every entry follows the posture: infrastructure only, never operations, fully disclosed, and for tribal work the Tribes lead and own everything.

- USDA Community Connect & Distance Learning/Telemedicine (FY2026 open, ~$44M combined) — deployment- and facility-shaped — viable only with a deployment partner (a rural utility cooperative or ISP builds; High Desert is community anchor). The cooperative kinship with Central Electric is the natural opening conversation

- The coalition path (join first) — the Oregon Broadband Equity Coalition — OSU Extension–led, free to join, with Tribal Nations, providers, and government at the table — is where rural and tribal connectivity work is coordinated and funded. Link Oregon (network services to tribal/education/nonprofit sectors) and Central Electric Cooperative (Redmond deployment partner) are the technical allies met through it. This network, not a cold application, is the credible entry to every line below

- State broadband set-asides (via Oregon Broadband Office) — the live channel for tribal-lands connectivity in 2026+ — the Warm Springs co-application pathway, with the Tribes as lead applicant and owner of all assets. The Warm Springs Community Action Team, a tribal-member-led nonprofit with grant capacity on staff, is the relationship through which this work eventually becomes real — on the Tribes’ timeline

- Federal tribal broadband (NTIA) — no open window in 2026; awarded tribes are in buildout. Watch for reopening; if it returns, it is the flagship tribal-program vehicle

- College-led federal education awards (NSF scholarship, technician-education, and two-year-college programs) — COCC and OSU-Cascades are developing a regional data-literacy and makerspace pathway funded through these institutional channels. High Desert is not the applicant — the honest role is named community partner: deployment sites, internship placements, letters of collaboration, and possibly a modest community-partner subaward. Value to High Desert: pipeline, equipment access, and credibility, not direct revenue

- Future Ready Oregon / state workforce funds (HECC) — earn-and-learn money for the internship program’s expansion, in partnership with COCC’s apprenticeship infrastructure and East Cascades Works (the regional workforce board) — moderate fit, pursue with the college or workforce board as lead. EDCO is the bridge to Business Oregon and the Oregon Innovation Council for any economic-development framing

- Meta Prineville Community Action Grants (~$1.4K–$30K observed; deadline ~November) — real money with a hard geographic rule: Crook County 501(c)(3)s and schools. Not available to High Desert today; becomes live when Prineville enters petition range or via a Crook County partner organization — flagged for the 2027–28 calendar, honestly conditional

# 04 — Resiliency Rules

- Dues fund core operations, always — if every grant vanished tomorrow, the platform runs

- No single funder exceeds 30% of annual revenue; government in total stays ≤25%

- Individual giving is cultivated as the third leg — target ≥15% of revenue by 2028; a hundred locals at $50 beats one foundation at $5,000 for both resilience and legitimacy

- Pipeline discipline — once eligible, keep at least three applications live at all times; never depend on any one decision

- No grant whose conditions touch the foundational commitments; every grant and its conditions published in the quarterly transparency report

- Renewal calendar — every award enters a calendar with its report dates and reapplication window the day it arrives

- Partner-as-route — for the ambitious work (connectivity, the bridge program, tribal infrastructure), pursue funding as a subawardee, co-applicant, or deployment partner through an established organization; shared funding is faster, more eligible, and more credible than leading alone, and the founding team states this openness plainly

## Revenue Mix Targets

| Year | Dues + Individual | Foundations | Government |
| --- | --- | --- | --- |
| 2026 | ~60–70% | ~30–40% (Roundhouse + locals) | 0% |
| 2027 | ~45–55% | ~45–55% (OCF, Collins, Ford) | 0% |
| 2028 | ~40%+ | ≤40% | ≤25%, infrastructure only |

# 05 — The 18-Month Funding Calendar

| When | Actions |
| --- | --- |
| June 2026 | Fiscal sponsor signed (local first, national fallback). Oregon DOJ registration. MyOCF account by June 18; OCF June 23 only if sponsorship closes in time. Roundhouse intro visit. Decide and document the sponsor’s admin fee in all budgets. |
| July 2026 | Roundhouse Small Grants LOI submitted (launch capacity, ~$12.5K). Ford Family program-officer call — settle the rural-eligibility frame; if green-lit, submit TA inquiry. Founding Supporters campaign built. |
| August 2026 | Roundhouse Fall Open Call application submitted (flagship two-year program, ~$48K). Press Forward JustFund profile created. |
| September 2026 | Form 1023 filed. CEC and First Interstate inquiries with the one-page case ($2–8K combined asks). |
| October 2026 | Public launch + Founding Supporters campaign live (goal $5–10K individual, receipts noting retroactive deductibility). Roundhouse Small Grant decision expected window opens. |
| November–December 2026 | Roundhouse Open Call decision window. Year-end giving push. OCF Spring 2027 application drafted from the Master Case (window opens ~Dec 1, closes mid-January). |
| Q1 2027 | OCF Spring application submitted by mid-January. Determination letter expected window begins — on arrival: Collins application out within 30 days; sponsor wind-down per agreement. |
| Q2–Q3 2027 | OCF decision (~May). Collins decision. Meyer opportunity evaluated against actual 2027 guidelines. Deschutes Cultural Coalition small grant (archive/heritage framing) if cycle aligns. First grant reports filed on time — the renewal calendar is now live. |
| Q4 2027 – 2028 | Renewals (Roundhouse year two, OCF after sit-out). Oregon Broadband Office relationship opened. College/makerspace MOUs signed; community-partner role in college-led federal proposals formalized. First Connect rural-access pilot grant assembled (USDA or state, with a cooperative deployment partner). Meta Prineville window evaluated if Crook County routing exists. Press Forward open calls watched; Compass joint concept ready if one fits. |

## Realistic Raise Projections

- 2026: $15K–$40K — Roundhouse small grant and/or Open Call, hyper-local checks, Founding Supporters

- 2027: $40K–$90K — OCF + Collins + Ford TA + renewals + individual growth

- 2028: $75K–$150K — diversified per the mix targets, internships and town #2 grant-funded

These are planning numbers, not promises — sized so that the budget ladder in the business plan works at the low end of every range.

HIGH DESERT · Funding Strategy & Pipeline v3 · June 2026